## Detailed Task Estimation
No: | Task Name | Task Type | Optimistic Effort(h) | Total Effort Estimation (P Hours) | 116
1 | Requirements |  |  | Estimator | Isanka Rathnayaka
2 | Initial Requirement Brainstoming - Identify user stories |  | 16 | Reviewer | Shanaka Perera
3 | Q & A Document prepartion and amend client feedback |  | 8
4 | Review & Clarification |  | 3
5
6 | Elaboration: System Design
7 | Backend:
| Identify domain entities | Requirement Dev | 8
8 | Identify core services | Design Development | 8
9 | Design solution hierarchy-folder structure & grouping | Design Development | 5
10 | Review & Rework | Design Development | 3
11
12 | Frontend:
13 | Sitemap - Landing page, Adming pages,…etc. | Requirement Dev | 16
14 | Angular module separation | Design Development | 10
15
16 | Implementation: Initial project structure
17 | Backend:
18 | Initial solution hierarchy and folder structure | Code Development | 4
19 | Identity provider-Initial configuration (Identity Server 4) | Code Development | 3
20
21 | Frontend:
22 | Web front end project initialization | Code Development | 1
23 | Component modularization | Code Development | 5
24 | Configure Routing | Code Development | 2
25
26 | OIDC client and Auth2
27 | Identity server - WebApi | Code Development | 8
28 | OICD client - Angular-web-front-end | Code Development | 8
29
30 | CI/CD Configuration | Code Development | 8
31 | Total Effort |  | 116
32

## Assumptions
Scope Related Assumptions
No. | Description
1 | End to end implementation is considered out of scope for this estimation.
2 | QA effort estimation is excluded at this stage as this is stage 0 & 1.
3 | Multiple language support is considered out of scope for this estimation.
4 | Test automation and application mobile device testing is considered out of scope at this stage of estimation.
5 | Staging and production environment configuration is considered out of scope at this stage.
6 | Cloud enviroment settings and configuration is considered out of scope.
Technical Assumptions
1 | Client should provide licencing cost for Visual studio 2019 and bare the cost for the staging and production environments.
2 | Client should provide the subscription or user account for Azure/AWS.
3 | Cloud service provider decision is considered out of scope as the initial design will be done to get the design compatible with the choosen cloud service provider.
General Assumptions
1 | Current estimation is based on the understanding of the given requirement/artifacts. And considered as the initial level 0 estimation. Hence, phase 2-level 2 effort will get subject to re-estimation.
2 | User acceptance criteria will be agreed after the requirement clarity meets a satisfactory level.